## Sheet1
Activity Types | Activities | 2021-07-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06
Lit. Review | Literature review of OpenSAFELY
Literature review of virus/covid research
Literature review around vaccines
Lit. review around covid and mental health
Literature review of long covid
Proposal | Project plan first draft write-up
Plan final draft write-up and submition
How do I define long covid
Data Exploration | E-mail OpenSAFELY team
Learning the OpenSAFELY software
Availability/format of data in Open SAFELY
Possible long COVID (based on symptoms)
Data Analysis | Corbidities with long covid
Medications with long covid
Long covid and mental health
Short covid vs. long covid
Cluster Analysis
Effect of vaccines on long covid
Data Polishing | Data visualisation
Interpretation of relevant results
Write-up | First draft write-up and review
Second draft write-up and review
Final draft write-up and review
Final Review and Submition
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15